## Slide 1: 120-Day Timeline for Success Adams Power
2/21/23
Initial Information Gathering
Strategy Development Exercise
Goals & Expectations Setting
RFP Content Development
2/27- 3/3/23
Alithias Care Navigator Set-up & Intro for March Safety Meeting
Fact-Finding Call- Amanda, Lori & Lisa
Review of The Doctor’s Office& Solstice Contract(s)
Introduction to Allegiance Team
Prep TPA/PBM Change for July 1st
  Weekly Date & Time Set
3/6- 3/24/23
Kick-Off Ticket Health Calls Weekly
Replacement of Supplemental Lines
Bio-metric Screening Prep and Dates Set
Network Comparison behind the scenes
Compliance Review
Employee Navigator Updates
3/27- 4/7/23
HSA Education Prep- April Safety Meeting
Plan Design & Benefit Guide Discussions
Compliance Review Continues
Continue Ticket Health Weekly Calls
Biometric Screenings Take Place
4/10- 4/21/23
Prep Open Enrollment Meetings
Weekly Ticket Health Calls Continue
Mental Health Partner Review
Care Navigator 1st Month Review

## Slide 2: 120-Day Timeline for Success(cont.) Adams Power
4/15/23
5/1/23
6/1/23 – 6/20/23
Implementation Kick-Off w/ Selected partner
Open Enrollment Timeline Finalization
Benefit & Plan Design Finalization
Benefit Booklets Created
Announcement Creation
Eligibility Carrier Integrations
Open Enrollment Done & Monitoring Of
Plan Design & Benefit Testing by Carriers
Loading & Verification
Plan Participant Communications
7/1/2023
and beyond
Partner Go-Live
ID Cards in-hand
Ongoing Plan Monitoring
Member Experience Monitoring
Finalization of Contract Negotiations
Formal Award of Business
Issuance of Termination (if necessary)
Contract Execution by Parties